# MEMORANDUM

TO: CEO & VP Growth

FROM: Jordan, Founding PM

DATE: March 16, 2026

RE: Q2 Conference Strategy & Recommendation

## Recommendation

I recommend Pawprint commit to Exhibiting at WVC Nashville 2026 (August) specifically within the "Start-up Zone." This option provides the highest lead generation potential (75-100 leads) at a lean cost (~$2,500), directly supporting our KR of 50+ new vet leads and the Q3 AI Symptom Checker launch.

## Option Comparison

| Option | Cost | Lead Potential | Resource Burden | Timeline |
| --- | --- | --- | --- | --- |
| Exhibiting | $2.5k - $5k | High | High | Feasible |
| Sponsorship | $5k - $15k | Medium | Low | High |
| Side Event | $3k - $8k | Medium | Extreme | Risky |

## Justification

- Strategic Alignment: Exhibiting allows us to demo the AI Symptom Checker urgency-level logic (Beta) directly to Practice Owners, our primary target.

- Efficiency: The "Start-up Zone" is $2.5k compared to $10k+ for general sponsorships. We hit our lead KRs without a significant burn increase.

- Market Data: Benchmarks show average cost-per-lead at trade shows is ~$112. With a $2,500 spend, we only need 23 leads to break even vs benchmarks; we project 75+.

## Key Risks

- Staffing: As a 12-person team, sending staff to Nashville strains operations. Mitigation: Send Jordan (PM) and 1 Growth lead only.

- Logistics: Exhibit logistics (shipping, A/V, collateral) require 3-4 months lead time. Mitigation: Secure Start-up Zone by April deadline.

## Next Steps

- Apply for WVC Start-up Zone by April 15.

- Design high-fidelity demo for AI Symptom Checker.

- Draft staffing and travel budget for approval.